## Product Backlog
US ID | Planned Sprint | Actual Sprint | Role | User Story Description | MoSCoW Priority | Acceptance Criteria | Dependency | Notes
A — Authentication & Onboarding
US01 | 1 |  | Citizen | As a citizen, I want to register on the platform by providing my name, phone number, address, email, and Aadhaar details so that I can access all civic reporting features. | Must Have | Verify all mandatory fields are validated before submission. Verify Aadhaar format is validated. Verify a confirmation email/SMS is sent on successful registration.
US02 | 1 |  | Organisation | As a public welfare organisation (NGO / student group / CSR), I want to register my organisation by submitting our details and type so that we can be reviewed for platform access. | Must Have | Verify org name, type, contact, and registration number are captured. Verify org status is set to 'Pending Approval' after submission. Verify the Super Admin receives a notification of the new request.
US03 | 1 |  | Solver | As a government department representative, I want to register my department on the platform so that we can be approved to receive and resolve civic complaints. | Must Have | Verify dept name, ministry/category, and contact details are captured. Verify account status is 'Pending Admin Approval' after submission.
US04 | 1 |  | User | As a user, I want to log in to my account using my registered email and password so that I can access my profile and activities. | Must Have | Verify login succeeds with valid credentials. Verify an error message is shown for invalid credentials. Verify account lockout after 5 failed attempts. | US01
US05 | 1 |  | User | As a user, I want to log in using SSO (Single Sign-On via Google or government ID portal) so that I can access the platform without managing a separate password. | Could Have | Verify SSO redirects correctly and returns a valid token. Verify SSO login creates or links an existing account. | US01
US06 | 1 |  | User | As a user, I want to log out of my account so that my session is securely terminated. | Must Have | Verify logout clears session data and redirects to the login page. Verify the user cannot access protected pages after logout. | US04
US07 | 1 |  | User | As a user, I want to change my password so that I can keep my account secure. | Should Have | Verify the current password is required before setting a new one. Verify the new password meets minimum strength requirements. | US04
US08 | 1 |  | User | As a user, I want to view and edit my profile details so that my personal information remains up to date. | Should Have | Verify all editable fields (name, phone, address) are saved correctly. Verify changes are reflected immediately on the profile page. | US04
US09 | 1 |  | User | As a user, I want to delete my account so that my personal data is permanently removed from the platform. | Could Have | Verify a confirmation prompt is shown before deletion. Verify all personal data is removed from the system upon confirmation. | US04
B — Super Admin
US10 | 1 |  | Admin | As a Super Admin, I want to review and approve or reject government department (Solver) registration requests so that only verified departments access the platform. | Must Have | Verify pending Solver registrations are listed in the Admin panel. Verify approval sends a confirmation notification to the Solver. Verify rejection sends a rejection reason to the Solver. | US03
US11 | 1 |  | Admin | As a Super Admin, I want to review and approve or reject public welfare organisation (PWG) registration requests so that only legitimate organisations are onboarded. | Must Have | Verify pending PWG registrations are listed in the Admin panel. Verify approval/rejection triggers a notification to the PWG. | US02
US12 | 1 |  | Admin | As a Super Admin, I want to view platform-wide statistics (total complaints, resolved, pending, active users) so that I can monitor platform health. | Should Have | Verify dashboard displays real-time counts of complaints by status. Verify active user counts are updated daily.
US13 | 1 |  | Admin | As a Super Admin, I want to deactivate or ban any user, solver, or PWG account so that I can enforce platform policy. | Should Have | Verify deactivated accounts cannot log in. Verify a reason for deactivation is recorded and communicated. | US10, US11
C — Complaint Lifecycle (Citizen)
US14 | 1 |  | Citizen | As a citizen, I want to report a civic issue by providing a title, description, category, image, location, and criticality level so that authorities can identify and address it. | Must Have | Verify all mandatory fields are validated before submission. Verify geolocation is extracted from the image or entered manually on a map. Verify the submitted complaint appears in the citizen's complaint history with status 'Submitted'. | US01
US15 | 1 |  | User | As a user, I want the system to automatically extract the description, department category, and geotag from a photo I upload so that I can report an issue faster. | Should Have | Verify ML extraction pre-fills description, category, and location fields. Verify the user can edit extracted fields before submitting. | US14 | ML-assisted
US16 | 1 |  | User | As a user, I want to view my complete complaint history (submitted, active, and resolved) in one place so that I can track all my reports. | Must Have | Verify all complaints are listed with their current status and last update date. Verify complaints can be sorted by date and filtered by status. | US14
US17 | 1 |  | User | As a user, I want to view the current status and timeline of a specific complaint so that I know exactly what progress has been made. | Must Have | Verify the complaint detail page shows a chronological status timeline. Verify solver remarks are visible on this page. | US16
US18 | 1 |  | User | As a user, I want to filter my complaints by status (active / resolved) and locality so that I can find the specific complaints I am looking for. | Must Have | Verify filters for status and locality work independently and in combination. Verify filter results update without a full page reload. | US16
US19 | 1 |  | User | As a user, I want to rate the resolution of a resolved complaint (1–5 stars) and optionally leave a comment so that I can provide feedback on the quality of the fix. | Should Have | Verify the rating option is only available for resolved complaints. Verify each complaint can only be rated once. Verify the rating is saved and visible on the complaint detail page. | US16
US20 | 1 |  | User | As a user, I want to re-open a resolved complaint and provide a reason if I am not satisfied with the resolution so that the issue can be reviewed and fixed properly. | Should Have | Verify re-open option appears after rating a complaint below 3 stars. Verify a reason field is mandatory for re-opening. Verify re-opened complaint status changes back to 'In Progress' and the solver is notified. | US19
US21 | 1 |  | User | As a user, I want to view all civic complaints reported around my locality on the home page so that I am aware of issues near me. | Should Have | Verify home page displays geo-filtered complaints based on user's registered address. Verify complaints can be filtered by active/resolved status and category. | US01
US22 | 1 |  | User | As a user, I want to financially support a civic issue by contributing funds towards its resolution so that resources are available to address it faster. | Could Have | Verify payment gateway integration processes contributions correctly. Verify the contributed amount is added to the issue's funding pool and visible on the complaint page. | US14
US23 | 1 |  | User | As a user, I want to receive an in-app and push notification when the status of my complaint changes so that I am always informed of progress. | Must Have | Verify notifications are triggered on every status change (Submitted → In Progress → Resolved → Re-opened). Verify notification includes the complaint ID and new status. | US14
US24 | 1 |  | User | As a user, I want to view issues recommended to me based on my interests and past activity so that I can discover and support relevant civic issues. | Could Have | Verify recommendations are personalised based on saved interests and complaint history. Verify the recommendations section is visible on the home page. | US29, US15 | Sprint 2 / ML
D — Scoreboard & Gamification
US25 | 1 |  | User | As a user, I want to view the global scoreboard showing top contributors (citizens and PWGs) ranked by their civic activity so that I am motivated to participate more. | Could Have | Verify scoreboard displays user/org name, rank, and contribution score. Verify the list can be filtered by locality.
US26 | 1 |  | User | As a user, I want to set my civic interests and preferred localities so that I receive relevant issue recommendations and can focus my contributions. | Should Have | Verify interests (by category) and localities can be selected and saved. Verify saved preferences are reflected in home page feeds and recommendations. | US01
US27 | 2 |  | Top Performer | As a top-performing user or PWG, I want to download a digitally signed achievement certificate when I reach a contribution milestone so that I can share my civic contribution. | Could Have | Verify certificate is auto-generated when a milestone threshold is reached. Verify certificate includes user name, milestone, and a unique verification code. Verify certificate is downloadable as a PDF. | US25
E — PWG / NGO / Student Group
US28 | 1 |  | PWG | As a PWG member, I want to log in to the platform after our organisation has been approved so that I can access and act on civic complaints. | Must Have | Verify PWG login is blocked until admin approval. Verify approved PWG can log in and access their dashboard. | US02, US11
US29 | 1 |  | PWG | As a PWG member, I want to view all active and resolved civic complaints on the platform so that I can identify issues our organisation can help address. | Must Have | Verify the complaints list is accessible to all approved PWG members. Verify complaints are visible with category, locality, and criticality. | US28
US30 | 1 |  | PWG | As a PWG member, I want to filter complaints by category, locality, and criticality so that I can efficiently find issues relevant to our expertise. | Should Have | Verify filter options include category, locality, and criticality. Verify combined filters return accurate results. | US29
US31 | 1 |  | PWG | As a PWG member, I want to submit a request to the relevant government department to participate in resolving a specific complaint so that we can contribute our resources. | Must Have | Verify a 'Request to Help' button is available on each open complaint. Verify the request is logged and a notification is sent to the assigned Solver. | US29
US32 | 1 |  | PWG | As a PWG member, I want to update the progress of a complaint assigned to our organisation so that the solver and citizen are kept informed. | Must Have | Verify progress update is available only for complaints our PWG has been approved for. Verify updates are logged in the complaint timeline visible to the solver and citizen. | US31
US33 | 1 |  | PWG | As a PWG member, I want to receive a notification when a solver approves or rejects our participation request so that we can plan our work accordingly. | Must Have | Verify in-app notification is sent immediately on solver decision. Verify notification states the complaint ID and decision. | US31
US34 | 1 |  | PWG | As a PWG member, I want to log out of my organisation's profile so that my session is securely ended. | Must Have | Verify logout clears the PWG session and redirects to the login page. | US28
US35 | 1 |  | PWG | As a PWG member, I want to view and update our organisation's profile details so that our information remains current on the platform. | Should Have | Verify all org profile fields are editable by the PWG admin member. Verify changes are saved and reflected on the profile page. | US28
F — Solver (Govt Dept)
US36 | 1 |  | Solver | As a solver, I want to log in to the platform after our department has been admin-approved so that I can access the complaints dashboard. | Must Have | Verify solver login is blocked until Super Admin approval. Verify approved solver can log in and access the complaint list. | US03, US10
US37 | 1 |  | Solver | As a solver, I want to receive a notification when a new complaint is routed to my department so that I can respond promptly. | Must Have | Verify in-app notification is triggered immediately when a complaint is assigned to the dept. Verify notification includes complaint ID, category, locality, and criticality. | US14, US36
US38 | 1 |  | Solver | As a solver, I want to view all complaints assigned to my department with their status, category, locality, and criticality so that I have a complete picture of pending work. | Must Have | Verify only complaints routed to this dept are visible. Verify each complaint shows status, category, locality, criticality, and submission date. | US36
US39 | 1 |  | Solver | As a solver, I want to filter complaints by status (active / resolved), locality, and criticality so that I can prioritise the most urgent work. | Must Have | Verify filters work independently and in combination. Verify filter results update accurately. | US38
US40 | 1 |  | Solver | As a solver, I want to update the status of a complaint (In Progress / Resolved / Rejected) and leave a remark so that citizens and stakeholders are kept informed. | Must Have | Verify status can be changed to In Progress, Resolved, or Rejected. Verify each status change is timestamped and logged in the complaint timeline. Verify a remark field is mandatory when rejecting a complaint. | US38
US41 | 1 |  | Solver | As a solver, I want to assign an estimated resolution time to a complaint so that citizens have a realistic expectation of when the issue will be fixed. | Should Have | Verify the estimated time field is editable on the complaint detail page. Verify the estimated date is displayed to the reporting citizen. | US38
US42 | 1 |  | Solver | As a solver, I want to view PWG participation requests for a complaint and approve or reject them so that I can control who assists in resolution. | Must Have | Verify participation requests appear in the Requests tab under each complaint. Verify approval sends a notification to the PWG. Verify rejection sends a reason notification to the PWG. | US31, US36
US43 | 1 |  | Solver | As a solver, I want to view a Requests tab with two sub-sections — PWGs requesting portal registration and PWGs requesting to help on specific complaints — so that I can manage all requests in one place. | Should Have | Verify the Requests tab has two clearly separated sub-sections. Verify each request can be approved or rejected with a reason. | US42
US44 | 1 |  | Solver | As a solver, I want to report a PWG for unsatisfactory or incomplete work on an assigned complaint so that quality standards are enforced. | Should Have | Verify a 'Report PWG' option is available for complaints with an assigned PWG. Verify the report is logged, sent to the Super Admin, and the PWG is notified. | US42
US45 | 1 |  | Solver | As a solver, I want to receive a notification when a citizen re-opens a resolved complaint so that I can review the dissatisfaction and take further action. | Should Have | Verify a notification is sent to the solver immediately when a complaint is re-opened. Verify the complaint status is updated to 'Re-opened' on the solver's dashboard. | US20, US36
US46 | 1 |  | Solver | As a solver, I want to view and update my department's profile details so that our contact and department information is current. | Should Have | Verify all dept profile fields are editable. Verify changes are saved and reflected on the profile. | US36
US47 | 1 |  | Solver | As a solver, I want to log out of my department profile so that my session is securely ended. | Must Have | Verify logout clears the solver session and redirects to the login page. | US36
G — Complaint Routing (System)
US48 | 1 |  | System | As the system, I want to automatically route a submitted complaint to the correct government department based on the issue category and locality so that no manual triage is required. | Must Have | Verify complaints are routed immediately upon submission. Verify routing logic maps each issue category to the correct dept. Verify the solver receives a new complaint notification on routing. | US14, US37
US49 | 1 |  | System | As the system, I want to detect duplicate complaints for the same issue in the same locality so that citizens are informed and solvers avoid duplicate work. | Should Have | Verify duplicate detection runs on complaint submission. Verify the submitting citizen is shown a notice if a similar open complaint exists nearby. Verify the citizen can choose to link to the existing complaint or submit separately. | US14
US50 | 1 |  | System | As the system, I want to auto-escalate a complaint to the Super Admin if it has been in 'In Progress' status for more than 30 days without resolution so that long-pending issues receive attention. | Should Have | Verify a background job checks complaint age daily. Verify escalation triggers a notification to the Super Admin and the solver. Verify the complaint is marked as 'Escalated' on the dashboard. | US40
H — ML Features (Sprint 2)
US51 | 2 |  | System | As the system, I want to use an ML algorithm to recommend relevant civic issues to each user based on their interests, location, and past activity so that high-impact complaints gain more visibility. | Could Have | Verify recommendations are personalised per user session. Verify the algorithm is re-evaluated when user activity or interests change. | US26 | Sprint 2
US52 | 2 |  | System | As the system, I want to predict the estimated time to resolve a complaint based on category, locality, and historical resolution data so that citizens and solvers get data-driven timelines. | Could Have | Verify the predicted timeline is displayed on the complaint detail page. Verify predictions are updated as resolution data grows. | US40 | Sprint 2
US53 | 2 |  | System | As the system, I want to predict the probability of a complaint being resolved within the estimated time so that stakeholders can assess its urgency and allocate resources accordingly. | Could Have | Verify a resolution probability score is displayed on the complaint detail page. Verify the score is recalculated each time the complaint status changes. | US52 | Sprint 2
US54 | 2 |  | System | As the system, I want to rank open complaints by priority score (derived from criticality, age, and funding support) so that solvers can address the most impactful issues first. | Could Have | Verify priority score is calculated and displayed on the solver's complaint list. Verify score factors are visible on hover/detail view. | US22, US14 | Sprint 2
I — Gap Stories (New)
US55 | 1 |  | Admin | As a Super Admin, I want to handle escalated complaints by reassigning them to a different government department or flagging them for urgent action so that long-pending issues are not ignored. | Should Have | Verify escalated complaints appear in a dedicated Admin queue. Verify Admin can reassign to a different dept with a reason note. Verify all parties (original solver, new solver, citizen) are notified on reassignment. | US50
US56 | 1 |  | Solver | As a solver, I want to view a complaint's funding pool amount so that I can factor available citizen financial support into resource planning. | Could Have | Verify the funding amount is visible on the complaint detail page. Verify funding total updates in real time as contributions are made. | US22, US38
US57 | 1 |  | User | As a user, I want to search for civic complaints by keyword, category, or locality so that I can quickly find a specific issue. | Should Have | Verify search returns results matching keyword in title or description. Verify category and locality filters can be combined with keyword search. Verify results are ranked by relevance. | US21
US58 | 1 |  | Citizen | As a citizen, I want to share a civic complaint on social media or via a link so that I can raise community awareness about an issue. | Could Have | Verify each complaint has a unique shareable URL. Verify share buttons for common platforms are available on the complaint detail page. | US14
US59 | 1 |  | User | As a user, I want to view a map-based view of all civic complaints in my area so that I can visually understand the geographic distribution of issues. | Should Have | Verify a map view is available on the home page and complaint list page. Verify each pin on the map represents a complaint and clicking it opens the complaint detail. | US21
US60 | 1 |  | Solver | As a solver, I want to upload photographic evidence when marking a complaint as resolved so that citizens and the admin can verify the fix. | Should Have | Verify a photo upload field is available when changing status to 'Resolved'. Verify uploaded photos are attached to the complaint timeline and visible to the citizen. | US40
US61 | 1 |  | User | As a user, I want to view the resolution photos uploaded by the solver when a complaint is marked resolved so that I can verify the fix before rating it. | Should Have | Verify resolution photos are displayed on the complaint detail page after resolution. Verify photos are visible before the user submits a rating. | US60, US19
US62 | 1 |  | PWG | As a PWG member, I want to upload evidence photos and progress notes when updating the status of a complaint we are working on so that the solver and citizen can track our work. | Should Have | Verify photo upload and notes field are available during progress updates. Verify uploads are added to the complaint timeline. | US32
US63 | 1 |  | Admin | As a Super Admin, I want to receive a notification when a solver files a report against a PWG so that I can review and take corrective action. | Should Have | Verify notification is triggered immediately on a PWG report being filed. Verify the Admin dashboard shows a 'PWG Reports' queue for review. Verify Admin can warn, suspend, or remove the PWG based on review. | US44
US64 | 1 |  | User | As a user, I want to view an FAQ and help guide on how to use the platform so that I can understand all features without needing support. | Could Have | Verify FAQ page is accessible from the main menu without login. Verify help content covers complaint submission, tracking, and rating flows.
US65 | 2 |  | System | As the system, I want to send a weekly digest notification to each citizen summarising new complaints in their locality and updates on their own complaints so that users stay engaged. | Could Have | Verify digest is generated every 7 days per user. Verify digest only includes complaints and updates relevant to the user's locality and interests. Verify users can opt out of digest notifications from profile settings. | US23, US26 | Sprint 2

## Platform Flow
Actor | Flow Step | Stories Covered
— REGISTRATION —
Citizen / PWG / Solver | Register on platform (separate forms per role) | US01, US02, US03
Super Admin | Reviews & approves Solver and PWG registrations | US10, US11
Citizen / PWG / Solver | Login → redirected to role-specific dashboard | US04, US28, US36
— COMPLAINT SUBMISSION —
Citizen | Fills complaint form: title, desc, category, image, location, criticality | US14
System | ML extracts metadata from image (dept, geotag, description) | US15
System | Checks for duplicate complaints in same locality | US49
System | Auto-routes complaint to correct Govt Dept based on category + locality | US48
Solver | Receives new complaint notification | US37
— SOLVER REVIEW & ASSIGNMENT —
Solver | Views complaint list — filters by status / locality / criticality | US38, US39
Solver | Updates status to 'In Progress', assigns estimated resolution time, adds remark | US40, US41
Citizen | Receives status change notification (In Progress) | US23
— PWG COLLABORATION —
PWG | Browses open complaints, filters by category/locality/criticality | US29, US30
PWG | Submits participation request to Solver for a specific complaint | US31
Solver | Reviews PWG requests in Requests tab — approves or rejects | US42, US43
PWG | Receives approval/rejection notification | US33
PWG | Works on complaint — uploads progress photos and notes | US32, US62
Solver | Monitors PWG progress; can report PWG for unsatisfactory work | US44
Admin | Receives PWG report notification; reviews and takes action | US63
— RESOLUTION —
Solver / PWG | Marks complaint as Resolved — uploads resolution photos | US40, US60
System | Triggers resolved notification to citizen | US23
Citizen | Views resolution photos, rates the resolution (1–5 stars) | US61, US19
Citizen | If unsatisfied (< 3 stars): re-opens complaint with reason | US20
Solver | Receives re-opened complaint notification | US45
— ESCALATION —
System | Auto-escalates complaint if unresolved > 30 days | US50
Admin | Reviews escalated complaints — reassigns dept or flags urgent | US55
— CITIZEN FEATURES —
Citizen | Views home page: locality map, complaint feed, recommendations | US21, US57, US59
Citizen | Tracks own complaints (history, status, timeline, remarks) | US16, US17, US18
Citizen | Financially supports an open complaint | US22
Citizen | Shares complaint via link or social media | US58
User | Views/filters global and locality scoreboard | US25
User | Sets interests and locality preferences for personalised feed | US26
Top Performer | Downloads achievement certificate on milestone | US27
— ML / SPRINT 2 —
System | Recommends issues to users based on interests and activity | US51
System | Predicts estimated resolution time per complaint | US52
System | Predicts resolution probability per complaint | US53
System | Ranks complaints by priority score for solvers | US54
System | Sends weekly locality digest to all users | US65
— ADMIN OVERSIGHT —
Admin | Monitors platform stats dashboard | US12
Admin | Deactivates/bans users, solvers, or PWGs for policy violations | US13

## Legend
Item | Meaning
Blue (BDD7EE) | Citizen / User / Organisation stories
Green (E2EFDA) | Solver / Govt Dept stories
Purple (D9D2E9) | PWG / NGO / Student Group stories
Orange (FCE4D6) | Super Admin stories
Red (F4B8B8) | System / ML stories
MoSCoW: Must Have | Core — must be delivered in sprint
MoSCoW: Should Have | Important — deliver if possible
MoSCoW: Could Have | Nice to have — deliver if capacity allows
MoSCoW: Won't Have | Out of scope for current sprints
Sprint 1 | Core platform features
Sprint 2 | ML/AI features and advanced gamification